## cost reference
Position | Typical_Salary | Lower_Bound | Upper_Bound
System Analyst | 700 | 500 | 800
Project Manager | 900 | 800 | 1100
Full Stack Developer (.NET/Java) | 900 | 700 | 1100
Data Engineer | 800 | 650 | 1050
Data Scientist | 1000 | 800 | 1300

## Gantt
Development Phase and Resource Deployment |  | Month | [11 empty] | Total Period | Cost Incurred
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
A. Requirement Definition and Data Preparation
| Project Manager | [12 empty] | 20 | 18000 | bar: Month 1
| System Analyst | [12 empty] | 20 | 14000 | bar: Month 1
| Data Engineer | [12 empty] | 20 | 16000 | bar: Month 1
B. Data Modelling
| Project Manager | [12 empty] | 20 | 18000 | bar: Month 2
| Data Scientist | [12 empty] | 20 | 20000 | bar: Month 2
| Data Engineer | [12 empty] | 20 | 16000 | bar: Month 2
C. Solution Development and Deployment
| Project Manager | [12 empty] | 20 | 18000 | bar: Month 3
| System Analyst | [12 empty] | 20 | 14000 | bar: Month 3
| Full Stack Developer (.NET/Java) | [12 empty] | 20 | 18000 | bar: Month 3
D. User Acceptance Testing
| Project Manager | [12 empty] | 14 | 12600 | bar: Month 4
| System Analyst | [12 empty] | 14 | 9800 | bar: Month 4
Total Cost | [14 empty] | 174400
9