## cost reference
Year | Position | Typical_Salary | Lower_Bound | Upper_Bound | Quantity | Incur_Period
0 | System Analyst | 700 | 500 | 800 | 1
0 | Business Analyst | 775 | 550 | 900 | 1
0 | Project Manager | 900 | 800 | 1100 | 1
0 | Full Stack Developer (.NET/Java) | 900 | 700 | 1100 | 1
0 | Data Engineer | 800 | 650 | 1050 | 1
0 | BI Developer | 775 | 600 | 900 | 1
0 | Data Scientist | 1000 | 800 | 1300 | 1

## Gantt
Development Phase and Resource Deployment |  | Week | [7 empty] | Total Period | Cost Incurred | Superannuation Adjustment
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
A. Requirement Definition, System Design and Data Preparation
| Project Manager | [8 empty] | 15 | 13500 | 15052.5 | bar: Week 1 to Week 3
| System Analyst | [8 empty] | 15 | 10500 | 11707.5 | bar: Week 1 to Week 3
| Data Engineer | [8 empty] | 15 | 12000 | 13380 | bar: Week 1 to Week 3
B. Data Modelling, Solution Development and Deployment
| Project Manager | [8 empty] | 20 | 18000 | 20070 | bar: Week 4 to Week 7
| Data Scientist | [8 empty] | 20 | 20000 | 22300 | bar: Week 4 to Week 7
| Data Engineer | [8 empty] | 20 | 16000 | 17840 | bar: Week 4 to Week 7
| System Analyst | [8 empty] | 20 | 14000 | 15610 | bar: Week 4 to Week 7
| Full Stack Developer (.NET/Java) | [8 empty] | 20 | 18000 | 20070 | bar: Week 4 to Week 7
C. User Acceptance Testing
| Project Manager | [8 empty] | 5 | 4500 | 5017.5 | bar: Week 8
| System Analyst | [8 empty] | 5 | 3500 | 3902.5 | bar: Week 8
Total Labor Cost | [10 empty] | 130000 | 144950
Contingency Reserve | [10 empty] | 20% | 28990
Total Cost | [11 empty] | 173940