## cost reference
Year | Position | Typical_Salary | Lower_Bound | Upper_Bound | Quantity | Incur_Period
0 | System Analyst | 700 | 500 | 800 | 1
0 | Project Manager | 900 | 800 | 1100 | 1
0 | Full Stack Developer (.NET/Java) | 900 | 700 | 1100 | 1
0 | Data Engineer | 800 | 650 | 1050 | 1
0 | Data Scientist | 1000 | 800 | 1300 | 1

## Gantt
Development Phase and Resource Deployment |  | Month | [11 empty] | Total Period | Cost Incurred
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
A. Requirement Definition, System Design and Data Preparation
| Project Manager | [12 empty] | 18 | 18063 | bar: Month 1
| System Analyst | [12 empty] | 18 | 14049 | bar: Month 1
| Data Engineer | [12 empty] | 18 | 16056 | bar: Month 1
B. Data Modelling
| Project Manager | [12 empty] | 20 | 20070 | bar: Month 2
| Data Scientist | [12 empty] | 20 | 22300 | bar: Month 2
| Data Engineer | [12 empty] | 20 | 17840 | bar: Month 2
C. Solution Development and Deployment
| Project Manager | [12 empty] | 20 | 20070 | bar: Month 3
| System Analyst | [12 empty] | 20 | 15610 | bar: Month 3
| Full Stack Developer (.NET/Java) | [12 empty] | 20 | 20070 | bar: Month 3
D. User Acceptance Testing
| Project Manager | [12 empty] | 6 | 6021 | bar: Month 4
| System Analyst | [12 empty] | 6 | 4683 | bar: Month 4
Total Cost | [14 empty] | 174832